## Sheet1
RESEARCH PROJECT PLAN |  | 2025 | [8 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
|  | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Project 1 | Literature Review | bar: 2025 A to 2025 A
Legacy data and MAUVE-MUSE datacube | bar: 2025 A
Stellar mass map | bar: 2025 M
SFR map | bar: 2025 M to 2025 J
rSFMS | bar: 2025 J to 2025 A
[O/H] map | bar: 2025 A
rMZR | bar: 2025 A to 2025 S
rFMR | bar: 2025 O to 2025 D
Paper 1 | bar: 2026 J to 2026 M
Project 2 | MAUVE-ALMA, dataset matching | bar: 2026 A to 2026 S
gas-FMR | bar: 2026 O to 2026 D
Paper 2 | bar: 2027 J to 2027 M
Project 3 | Stellar population map | bar: 2027 A to 2027 J
stellar-FMR | bar: 2027 J to 2027 S
Further analysis | bar: 2027 O to 2027 D
Paper 3 | bar: 2028 J to 2028 M
Presentations | 6-month Review | bar: 2025 A
Annual Reviews | bar: 2026 M; 2027 M; 2028 M
Thesis | bar: 2028 A to 2028 S
RESEARCH TRAINING PLAN |  | 2025 A: 2025; 2026 J: 2026; 2027 J: 2027; 2028 J: 2028
|  | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Milestone | Research Proposal | bar: 2025 A
Annual Report 1 | bar: 2026 M
Annual Report 2 | bar: 2027 M
Annual Report 3 | bar: 2028 M
Coursework Units | GRC induction | bar: 2025 A
GRC welcome | bar: 2025 A
Academic Conduct and Research Integrity (ACRI9000) | bar: 2025 A
Science Communication for Astrophysicist (PHYS5003) | bar: 2025 A to 2025 J
Professional Development | Conferences | bar: 2026 J; 2027 J; 2028 J