## Sheet1
RESEARCH PROJECT PLAN |  | 2025 | [10 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028
|  | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | J | F | M | A | M | J | J
Project 1 | Literature Review | bar: 2025 F to 2025 D
Prepare for FLAMINGO cluster dataset | bar: 2025 M to 2025 M
Reconstruct galaxy cluster evolution | bar: 2025 J to 2025 A
Quantify the gas distriibution | bar: 2025 S to 2025 D
Analyse the relation between distribution and the evolution | bar: 2026 J to 2026 F
Find observables | bar: 2026 J to 2026 A
Paper | bar: 2026 M to 2026 O
Project 2 | Quantify the star distriibution | bar: 2026 N to 2027 M
Analyse the relation between distribution and the evolution | bar: 2027 F to 2027 A
Find observables | bar: 2027 A to 2027 J
Paper | bar: 2027 J to 2027 A
Project 3 | Prepare for FLAMINGO group dataset | bar: 2027 S to 2027 N
Estimate contribution from the HI within the stellar disc to HIMF | bar: 2027 N to 2028 J
Paper | bar: 2028 J to 2028 A
Presentations | Research proposal seminar | bar: 2025 A
Annual reviews | bar: 2026 F; 2027 F; 2028 F
Thesis | bar: 2028 J to 2028 J
RESEARCH TRAINING PLAN |  | 2026 J: 2024; 2027 J: 2025; 2028 J: 2026
|  | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | J | F | M | A | M | J | J
Milestone | Research Proposal | bar: A
Annual Report 1 | bar: 2024 F
Annual Report 2 | bar: 2025 F
Annual Report 3 | bar: 2026 F
Coursework Units | GRC induction | bar: F
GRC welcome | bar: M
Academic Conduct and Research Integrity (ACRI9000) | bar: M
science Communication for physicist | bar: A to J
Professional Development | ASA annual meeting | bar: M; 2024 J; 2025 S
* The GANTT chart is an example timeline for a full time PhD student commencing in JAN 2019. Readjust the dates according to the date of your enrolment, the course you are enrolled in (2y Masters, 3y PhD), and your course enrolment type (full time or part time).
** Columns A&B, Rows 3-32, are suggestions only. Add, delete or change row headings as required for your particular project needs. For example, deleting ethics approval requirement, adding research parts, and/or changing the types of training you intend to complete.
Chart Orginally from Seona Lee
›